## Slide 1: MUVA MIS
Conceptual Design
Andres, Paul, Kerry
March, 2022

## Slide 2: Objectives
Brief description of the current system
Define the conceptual scope of the new MIS
Elements and components
Indicators for dashboard
Map of potential responsibilities
Pilot
Software, Costs, and Team

## Slide 3: Current Data System
Software | Mobilization | Registration | Num + Lit | FH | Other tests | *Selection | Turmas | Attendance | Transfers | Project Info | Partners | Operational
Survey Solutions |  |  | S | S | S |  |  |  | ? |  |  | 
MIS LINK |  |  | S | S | S |  |  |  |  |  |  | 
Zoho Creator |  |  |  | S |  |  |  | R |  |  |  | 
Paper (?) |  |  |  |  |  |  |  |  |  |  |  | 
Excel & Other |  |  |  |  |  |  |  |  | ? | ? | ? | ?
*S or R indicate that the process relies in Stata or R to conduct the analysis

## Slide 4: Scope of the new MIS
Unify MUVA’s data management system
Follow participants over time (Unique MUVA ID)
Allow a friendly query of the data
Facilitate ongoing learning via a dashboard (attendance/transfers)
Organize programme’s data (projects, parceiros, financiadores, operational data)
Avoid duplication and conflicts between versions

## Slide 5: Conceptual Design
Phase 1

## Slide 6: Conceptual Design

## Slide 7: Software
Zoho creator: create an account for MUVA and set credentials to allow the creation of users, pages, reports (about 240 EUR/month)
A server to host dashboards and a domain for the data entry.(currently using mine) (about 20 EUR/month)
Survey Solutions server (about 20 EUR /month). Ccurrently using mine
Stata/R

## Slide 8: Team/responsibilities
Developers: Andres, Dercio, Tercio, Manuel (?)
Enters data for MEL: MEL team, Manuel QA’s
Enters data for sistemico: PM of each project, (?) supervises
Enters data for attendance: facilitators
Audience of dashboards: Implementing teams

## Slide 9: Pilot phase
Log all MUVA projects and test which information is relevant
Choose 2 active projects
Test the unique ID system
Test ongoing monitoring of attendance or transfers
Test process of ongoing learning
Test rastreamiento sistemico

## Slide 10: TBD
Process to follow project cycle in the MIS (what to do internally and what externally)
Train users and define data protocols (analysis, storing, updating)
Ideas for rapid follow-ups (?)
If phase 1 works, strategy to escalate and to grow the system